## Pre-Registration NFR Testing
Pre-Reg Scope & Test Plan
Sl. No. | SL.No. | Entities | Activities | #Concurrent Users | Duration | #Tests | Defect Ids | Status without volume | Volume | Status with volume
1 | 1 | UI | Performance & Load Testing | 100 | 1 hr | 1. 100 users | 1)MOS-27246 -Observed high response times for Homepage and Logout pages 2)MOS-25525 -Continue button functionality in Booking appointment page is broken in Performance environment(pt.mosip.io) 3)MOS-24804 -Observing "encryption failed" error messages in Pre-reg performance environment | completed | 1 month data | Pending
|  |  |  | 200 |  | 2. 200 users | 4)MOS-25581 -Observing high response times and error rate for 200 concurrent users in performance environment ¦6th June 5)MOS-27273 -Exception occurred in HDFs adapter -200 concurrent users test 6)MOS-27246 -Observed high response times for Homepage and Logout pages for 200 concurrent users 7)MOS-27275 -Observing invalid response for notification requests | completed |  | Pending
|  |  |  | 500 |  | 3. 500 users |  | Pending |  | Pending
|  |  |  | 1000 |  | 4. 1000 users |  | Pending |  | Pending
|  |  |  | 1500 |  | 5. 1500 users |  | Pending |  | Pending
|  |  |  | 2600 (Peak Load) |  | 6. 2600 users |  | Pending |  | Pending
2 | 2) | UI | Stress Testing | 5200 (Twice the peak concurrent users) | 1 hr | 1 |  | Pending | 1 month data (min) | Pending
3 | 3) | UI | Endurance Testing | 1950 (75% of peak concurrent users) | 12 hrs | 1 |  | Pending | 1 month data (min) | Pending
4 | 4) | UI | Performance & Load Testing | 2600 | 1 hr | 1 |  | Pending | 6 month data | Pending
5 | 5) | UI | Performance & Load Testing | 2600 | 1 hr | 1 |  | Pending | 1 year data | Pending
6 | 6) | Back job - Slot availability | Performance & Load Testing | NA | 1 hr | 1. 30 days slot avalability test | 8)MOS-24933 -slot avalability batch job for 30 days is not working in performance environment (pt.mosip.io) | completed | 1 month data in reg_available_slot table After every slot creation exercise we are creating appointment volumes just to make it a 1 hr test | Pending
[6 empty] | 2. 60 days slot avalability test | 9)MOS-25468 -60 days Slot availability batch job execution end status is showing as "NULL" and exit code is "UNKNOWN" in performance environment | completed
[6 empty] | 3. 90 days slot avalability test |  | completed
[6 empty] | 4. 120 days slot avalability test |  | completed
[6 empty] | 5. 150 days slot avalability test |  | completed
[6 empty] | 6. 180 days slot avalability test |  | completed
7 | 7) | Back job - Expiry of appointment | Performance & Load Testing | NA | NA | 1. 10% of peak pre-registrations per day (20800) |  | completed | 1-6 month data in the applicant_demographic table | Pending
[6 empty] | 2. 20% of peak pre-registrations per day (20800) |  | completed |  | Pending
[6 empty] | 3. 30% of peak pre-registrations per day (20800) |  | completed |  | Pending
8 | 8) | Back job - consumed batch job | Performance & Load Testing | NA | NA | 1. 10% of peak registrations per day (30000) are cancelled 90% (27000) are marked CONSUMED | 10)MOS-25723 -Consumed batch job execution end status is showing as "UNKNOWN" and exit code is "FAILED" in performance environment | completed | 1-6 month data in the applicant_demographic_consumed, applicant_document_consumed tables | Need to repeat the test with the volumes created
[6 empty] | 2. 20% of peak registrations per day (30000) are cancelled 80% (24000) are marked CONSUMED |  | Pending |  | Pending
UI scenarios and Percentage users distribution
| Sl No | Scenario Name | Projetced Users as per workload Doc (2600 users) | Percentage of Users
| 1 | Appointment booking full flow | 650 | 25%
| 2 | Enter demographic detail (New users) | 260 | 10%
| 3 | Edit demographic details (Existing Users) | 260 | 10%
| 4 | Appointment booking for an existing application (Existing Users) | 390 | 15%
| 5 | delete an application | 130 | 5%
| 6 | Appointment booking for application which has POI and POA docs already uploaded (Existing Users) | 130 | 5%
| 8 | cancel appointment | 130 | 5%
| 9 | View acknowledgement | 260 | 10%
| 10 | Appointment Rebooking for another time slot | 364 | 15%
Batch Job scenarios and Percentage users distribution
| 1) | Slot avalabilty batch Job
i)Slot avalabilty for 1 month
ii)Slot avalabilty for 2 months
iii)Slot avalabilty for 3 months
iv)Slot avalabilty for 4 months
v)Slot avalabilty for 5 months
vi)Slot avalabilty for 6 months
| 2) | Expiry batch job
i)Expiring 10% of Peak enrollments per hour in workload modelling is 20800 (Per hour is 2600)
ii)Expiring 20% of Peak enrollments per hour in workload modelling is 20800 (Per hour is 2600 )
iii)Expiring 30% of Peak enrollments per hour in workload modelling is 20800 (Per hour is 2600 )
| 3) | Consumed batch job
i)running a batch job for 90% consumed status and 10% cancelled enrollments status
ii)running a batch job for 80% consumed status and 20% cancelled enrollments status

## Reg-Processor NFR Testing
Registration-Processor Scope and test Plan
Sl. No. | Entities | Activities | #Concurrent Users | Details | Duration | #Tests | Defect ID | Volume | Status
1 | Reg Proc Module | Performance & Load Testing (Stage I-upload of packets) Users=Reg client threads uploading packets | 50 Users | 1. Approx number of packets created per day per operator - 35 2. Registration per day - 30000 3. Number of registration kiosks ~ 30000/35=860 ~ 900 | 1 hr | 1 | MOS-26862 -Sync-registration service is not working in performance environment MOS-27298 -Error related to mismatch of hashcode coming during performanc test of packet upload API MOS-27000-There is no validation check for the registration id present in packet meta info file and registration id of packet | NA | Done (without Volume)
2 |  |  | 100 Users |  |  | 1 |  | 1 month data (9 Lakh registrations=30000 reg per day * 30 days) Volume is to be created using Jmeter script and DBA scripts in all Reg Proc Tables | Pending
3 |  |  | 200 Users |  |  | 1 |  | 1 month data and the data created by earlier tests 960000 | Pending
4 |  |  | 500 users |  |  | 1 |  | 1 month data and the data created by earlier tests 990000 | Pending
|  |  | 900 users with mixed registrations types (NEW, UPDATE, LOST, ACTIVATE, DEACTIVATE) |  |  | 1 |  | 1 month data (1020000+30000 = 1050000) | Pending
6 |  | Stress Testing (twice the peak load) | 1800 |  | 1 hr | 1 |  | 1080000 registrations in DB | Pending
7 |  | Endurance Testing (with 75% of peak load users) | 630 |  | 8 hr | 1 |  | 1110000 registrations in DB | Pending
8 |  | Performance & Load Testing (Stage II-packet processing) | 900 (peak load) |  | 1 hr | 1 |  | 6 month data ( 900000 * 6 = 5.4 million records) | Pending
9 |  |  | 900 (peak load) |  | 1 hr | 1 |  | 12 month data (10.8 million records) | Pending
1. 30000 packets are considered to be uploaded in 1 hour of the day 2. 8 hours of working is cnsidered in a day 3. For now, sync of packets is considered to be one packet per sync for th packet generation utility 4. Below is the list of all the APIs related to registration processor mapped as covered/not covered as part of performance testing
SL.No. | Service | sub services | Register processor API's | Performance testing covered or not
1 | Packet receiver Service |  | https://mosip.io/registrationprocessor/v1/packetreceiver/registrationpackets | Covered
2 | Registration Status Service | 2.1) Packet-status service | POST/registrationprocessor/v1/registrationstatus/search | Covered
|  | 2.2) Sync-registration service | https://mosip.io/registrationprocessor/v1/registrationstatus/sync | Covered
3 | Manual Adjudication Service | 3.1) manual-adjudication-assignment service | https://mosip.io/registrationprocessor/v1/manualverification/assignment | TBD
|  | 3.2) manual-adjudication-decision service | post /registrationprocessor/v1/manualverification/decision | TBD
|  | 3.3) manual-adjudication-applicant-biometric service | https://mosip.io/registrationprocessor/v1/manualverification/applicantBiometric | TBD
|  | 3.4) manual-adjudication-applicant-demographic service | POST /registrationprocessor/v1/manualverification/applicantDemographic | TBD
|  | 3.5) manual-adjudication-packet-metainfo service | POST /registrationprocessor/v1/manualverification/packetInfo | TBD
4 | Bio Dedupe Service | 4.1) Bio Dedupe service | GET /registrationprocessor/v1/bio-dedupe/{referenceid} | Not Covered
5 | Packet Generator Service | 5.1) Packet Generator Service | POST /registrationprocessor/v1/packetgenerator/registrationpacket | Not Covered

## IDA NFR Testing
IDA Scope and test Plan
Sl. No. | Entities | Activities | #Concurrent Users | Details | Duration | #Tests | Defect ID | Volume | Status
1 | IDA Authentication | Performance & Load Testing | 100 Users | Target to achieve 12 TPS (4200 Tr per hour) | 1 hr | 1 |  | 1 month data created by the traffic of registration processor (i.e 900000 id repo records)
2 | IDA e-KYC |  | 100 Users | Target to achieve 12 TPS (4200 Tr per hour) |  | 1 |  | 1 month data created by the traffic of registration processor (i.e 900000 id repo records) | Pending
|  | Stress Testing (twice the peak load ~ throughput) | 200 Users | Target to achieve 24 TPS (8400 Tr per hour)
6 |  | Stress Testing (twice the peak load ~ throughput) | 200 users | Target to achieve 24 TPS (8400 Tr per hour) | 1 hr | 1 |  | 1 month data created by the traffic of registration processor (i.e 900000 id repo records) nd the volumes created by previous tests | Pending
7 |  | Endurance Testing (with 75% of peak load users) | 75 users |  | 12 hr | 1 |  | 1 month data created by the traffic of registration processor (i.e 900000 id repo records) nd the volumes created by previous tests | Pending
8 |  | Performance & Load Testing (Stage II) | 100 (peak load) |  | 1 hr | 1 |  | 6 month data ( 900000 * 6 = 5.4 million records) | Pending
9 |  |  | 100 (peak load) |  | 1 hr | 1 |  | 12 month data (10.8 million records) | Pending
| Auth transactions per day | 500000 |  | KYC transactions per day | 500000
| Working hours in a day | 12 |  | Working hours in a day | 12
| Transactions per hour | 41666.6667 |  | Transactions per hour | 41666.6667
| Transactions per second | 11.5741 |  | Transactions per second | 11.5741
| Response time SLA for REST APIs | 3 seconds |  | Response time SLA for KYC REST APIs | 3 seconds
Distribution across auth requests
|  | % transactions | Transactions per day | Transactions per hour | Transactions per second | Think Time (Expected) | Response Time(SLA) | Target Users | Whole number of users
| demo+uin( DOB+ name) | 25% | 125000 | 10416.6667 | 2.8935 | 5000 | 3000 | 23.1481 | 24
| otp+uin | 10% | 50000 | 4166.6667 | 1.1574 | 5000 | 3000 | 9.2593 | 10
| demo+vid (address + DOB) | 25% | 125000 | 10416.6667 | 2.8935 | 5000 | 3000 | 23.1481 | 24
| otp+vid | 10% | 50000 | 4166.6667 | 1.1574 | 5000 | 3000 | 9.2593 | 10
| demo+otp+uin (fullname) | 15% | 75000 | 6250 | 1.7361 | 5000 | 3000 | 13.8889 | 14
| demo+otp+vid (fullname) | 15% | 75000 | 6250 | 1.7361 | 5000 | 3000 | 13.8889 | 14
96
Distribution across e-KYC requests
|  | % transactions | Transactions per day | Transactions per hour | Transactions per second | Think Time (Expected) | Response Time(SLA) | Target Users | Whole number of users
| ekyc+otp+uin | 50% | 250000 | 20833.3333 | 5.787 | 5000 | 3000 | 46.2963 | 47
| ekyc+otp+vid | 50% | 250000 | 20833.3333 | 5.787 | 5000 | 3000 | 46.2963 | 47