## Pre-Reg NFR Testing
Pre-Registration Scope & Test Plan
Sl.No. | Entities | Activities | #Concurrent Users | Duration | #Tests
1 | UI | Performance & Load Testing | 100 | 1 hr | 1. 100 users
|  |  | 200 |  | 2. 200 users
|  |  | 500 |  | 3. 500 users
|  |  | 1000 |  | 4. 1000 users
|  |  | 1500 |  | 5. 1500 users
|  |  | 2600 (Peak Load) |  | 6. 2600 users
2 | UI | Stress Testing | 5200 (Twice the peak concurrent users) | 1 hr | 1
3 | UI | Endurance Testing | 1950 (75% of peak concurrent users) | 12 hrs | 1
4 | UI | Performance & Load Testing | 2600 | 1 hr | 1
5 | UI | Performance & Load Testing | 2600 | 1 hr | 1
6 | Back job - Slot availability | Performance & Load Testing | NA | 1 hr | 1. 30 days slot avalability test 2. 60 days slot avalability test 3. 90 days slot avalability test 4. 120 days slot avalability test 5. 150 days slot avalability test 6. 180 days slot avalability test
7 | Back job - Expiry of appointment | Performance & Load Testing | NA | NA | 1. 10% of peak pre-registrations per day (20800) 2. 20% of peak pre-registrations per day (20800) 3. 30% of peak pre-registrations per day (20800)
8 | Back job - consumed batch job | Performance & Load Testing | NA | NA | 1. 10% of peak registrations per day (30000) are cancelled 90% (27000) are marked CONSUMED 2. 20% of peak registrations per day (30000) are cancelled 80% (24000) are marked CONSUMED
UI scenarios and Percentage users distribution
Sl No | Scenario Name | Projetced Users as per workload Doc (2600 users) | Percentage of Users
1 | Appointment booking full flow | 910 | 35%
3 | Edit demographic details (Existing Users) | 260 | 10%
4 | Appointment booking for an existing application (Existing Users) | 390 | 15%
5 | Cancel and delete an application | 260 | 10%
6 | Appointment booking for application which has POI and POA docs already uploaded (Existing Users) | 130 | 5%
7 | View acknowledgement | 260 | 10%
8 | Appointment Rebooking for another time slot | 364 | 15%
Batch Job scenarios and Percentage users distribution
1 | Slot avalabilty batch Job
i)Slot avalabilty for 1 month
ii)Slot avalabilty for 2 months
iii)Slot avalabilty for 3 months
iv)Slot avalabilty for 4 months
v)Slot avalabilty for 5 months
vi)Slot avalabilty for 6 months
2 | Expiry batch job
i)Expiring 10% of Peak enrollments per hour in workload modelling is 20800 (Per hour is 2600)
ii)Expiring 20% of Peak enrollments per hour in workload modelling is 20800 (Per hour is 2600 )
iii)Expiring 30% of Peak enrollments per hour in workload modelling is 20800 (Per hour is 2600 )
3 | Consumed batch job
i)running a batch job for 90% consumed status and 10% cancelled enrollments status
ii)running a batch job for 80% consumed status and 20% cancelled enrollments status

## Reg-Proc NFR Testing
Registration-Processor Scope and test Plan
Sl. No. | Entities | Activities | #Concurrent Users | Details | Duration
1 | Reg Proc Module | Performance & Load Testing (Stage I-upload of packets) Users=Reg client threads uploading packets | 50 Users | 1. Approx number of packets created per day per operator - 35 2. Registration per day - 30000 3. Number of registration kiosks ~ 30000/35=860 ~ 900 | 1 hr
2 |  |  | 100 Users
3 |  |  | 200 Users
4 |  |  | 500 users
6 |  | Stress Testing (twice the peak load) | 1800 |  | 1 hr
7 |  | Endurance Testing (with 75% of peak load users) | 630 |  | 8 hr
8 |  | Performance & Load Testing (Stage II-packet processing) | 900 (peak load) |  | 1 hr
9 |  |  | 900 (peak load) |  | 1 hr
1. 30000 packets are considered to be uploaded in 1 hour of the day 2. 8 hours of working is cnsidered in a day 3. For now, sync of packets is considered to be one packet per sync for th packet generation utility 4. Below is the list of all the APIs related to registration processor mapped as covered/not covered as part of performance testing
SL.No. | Service | Sub Services | Registeration Processor API's | Performance testing covered or not
1 | Packet receiver Service |  | https://mosip.io/registrationprocessor/v1/packetreceiver/registrationpackets | Covered
2 | Registration Status Service | 2.1. Packet-status service | POST/registrationprocessor/v1/registrationstatus/search | Covered
|  | 2.2. Sync-registration service | https://mosip.io/registrationprocessor/v1/registrationstatus/sync | Covered

## IDA NFR Testing
IDA Scope and test Plan
Sl. No. | Entities | Activities | #Concurrent Users | Details | Duration | #Tests
1 | IDA Authentication | Performance & Load Testing | 100 Users | Target to achieve 12 TPS (4200 Tr per hour) | 1 hr | 1
2 | IDA e-KYC |  | 100 Users | Target to achieve 12 TPS (4200 Tr per hour) |  | 1
3 |  | Stress Testing (twice the peak load ~ throughput) | 200 Users | Target to achieve 24 TPS (8400 Tr per hour)
4 |  | Stress Testing (twice the peak load ~ throughput) | 200 users | Target to achieve 24 TPS (8400 Tr per hour) | 1 hr | 1
5 |  | Endurance Testing (with 75% of peak load users) | 75 users |  | 12 hr | 1
6 |  | Performance & Load Testing (Stage II) | 100 (peak load) |  | 1 hr | 1
7 |  |  | 100 (peak load) |  | 1 hr | 1
| Auth transactions per day | 500000 |  | KYC transactions per day | 500000
| Working hours in a day | 12 |  | Working hours in a day | 12
| Transactions per hour | 41666.6667 |  | Transactions per hour | 41666.6667
| Transactions per second | 11.5741 |  | Transactions per second | 11.5741
| Response time SLA for REST APIs | 3 seconds |  | Response time SLA for KYC REST APIs | 3 seconds